## Sheet1
IS&T RASCI Matrix
This matrix documents the responsibility assignments (namely Responsible, Accountable, Support, Consulted, and Informed) for deliverables, milestones, and tasks related to application software change efforts as defined in the revised IS&T SDLC. SDLC Effort Types covered by this matrix include all efforts that IS&T is directly managing (for example,Project Management Office (PMO) run projects are not covered). Typically this would be Production Incident Resolution, Maintenance, and Enhancements. This matrix includes the minimum required inclusion of those that must be supported, consulted and informed, but each change effort may choose to expand those participants as necessary.
Level of Responsibility
R = Responsible | Responsible - the person who actually owns the project, task, or work. An example would be the Project Manager.
A = Accountable | Accountable - The person who is ultimately responsible for the project/task/resources
S = Support | Support - People who will provide help to the Responsible person.
C = Consulted | People who has the ability or knowledge needed to complete the work and assist the Responsible and Supporting persons.
I = Informed | People who must be kept informed of the work, but not necessarily consulted
Deliverables Milestones Tasks | Business |  |  | IS&T | [12 empty] | Privacy & Security |  | Procurement & Contract Management
| Project Sponsor | IT Governance Committee | Service Owner (Aaron) | IS&T Division | Chief Information Officer (CIO) | Project Management Office Director(PMO) | Budget Officer | Application Manager | Project Manager | Business Analyst | Technical Architect | Technical Support Team (Cedrc, Bill) | UAT Test Coordinator | Test Lead | Tester | Help Desk Support | Privacy and Security Office | Security Analyst
Effort Artifacts (as required per revised IS&T SDLC)
Business Concept Stage
IT Governance Committee: Business Concept
Initiation Stage
Project Charter
Detailed Project Budget
Cost Benefit Analysis
Project Schedule
Privacy Threshold Anlaysis
Planning & Design Stage
Requirements Document
Impact Assessment
Requirements Traceability Matrix
Request for Proposal
Project RFP Review
Project Charter(refined and baseline)
Detailed Project Budget (refined and baseline)
Project Financial Assessment (refined and baseline)
Project Schedule (refined and baseline)
Vendor Project Management Plan
Communication Plan and Communications Matrix
Risk and Issue Management Plan
Risk & Issue Log
Change Management Plan, Change Request Form, and Change Request Log
Steering Committee Charter
Quality Plan
Technical Architecture System Design
Security Plan
Project Security Review Form
Test Plan
Training Plan
Project Peer Review Form
Disaster Recovery Plan
Execution & Build Stage
User Acceptance Testing Test Cases/ Test Scripts
Requirements Traceability Matrix (Refined)
Technical Test Results
User Acceptance Testing Results
Requirements Document (Refined)
Detailed Design Specifications (Refined)
UAT Acceptance
Operations and Maintenance Plan
Training Materials (format as needed)
User Documentation/ Online Help (format as needed)
Pilot Results
Go-Live Readiness Assessment Form
Implementation Stage
Requirements Document (Refined)
Transition Plan
Closeout Stage
Lessons Learned
Closeout Report